## Scheduled Job
PeriodEnd | Case Code | Case Name | Location | Lead IP | Manager | Appointment Date | Case Type | Due | Description | Class | Status | Done Date | Who By | Progress | Late Reason | Note | Closed | dateupdated | In or Out of control | Comments
2021-07-31 | HOLD00L | Holdio Eagle LLP | LONDON | Stephen Roland Browne | Calum Leslie | 2020-12-15 | MVL | 2020-12-28 | Confirm date GM resolution, notice of the liquidator's appointment and creditor's notice to claim was advertised in Gazette | 01 | D | 2021-01-04 | gdickenson | Notice was sent to courts on 18/12/20 but not advertised until 04/01/21 due to human error made by courts | An email was sent to Courts on 18/12/20 to advertise the notice but the request was not completed due to human error by them-advert date was 4/1/21 |  |  | 2021-07-30 16:20 | No Breach
2021-07-31 | HOLD01L | Holdio Holdco Limited | LONDON | Stephen Roland Browne | Calum Leslie | 2020-12-15 | MVL | 2020-12-28 | Confirm date GM resolution, notice of the liquidator's appointment and creditor's notice to claim was advertised in Gazette | 01 | D | 2021-01-04 | gdickenson | Notice was sent to courts on 18/12/20 but not advertised until 04/01/21 due to human error made by co | An email was sent to Courts on 18/12/20 to advertise the notice but the request was not completed due to human error by them-advert date was 4/1/21 |  |  | 2021-07-30 16:20 | In
2021-07-31 | HOLD02L | Holdio Interco Limited | LONDON | Stephen Roland Browne | Calum Leslie | 2020-12-15 | MVL | 2020-12-28 | Confirm date GM resolution, notice of the liquidator's appointment and creditor's notice to claim was advertised in Gazette | 01 | D | 2021-01-04 | gdickenson | Notice was sent to courts on 18/12/20 but not advertised until 04/01/21 due to human error made by co | An email was sent to Courts on 18/12/20 to advertise the notice but the request was not completed due to human error by them-advert date was 4/1/21 |  |  | 2021-07-30 16:20 | No Breach
2021-07-31 | HOLD03L | Holdio Midco Limited | LONDON | Stephen Roland Browne | Calum Leslie | 2020-12-15 | MVL | 2020-12-28 | Confirm date GM resolution, notice of the liquidator's appointment and creditor's notice to claim was advertised in Gazette | 01 | D | 2021-01-04 | gdickenson | Notice was sent to courts on 18/12/20 but not advertised until 04/01/21 due to human error made by co | An email was sent to Courts on 18/12/20 to advertise the notice but the request was not completed due to human error by them-advert date was 4/1/21 |  |  | 2021-07-30 16:20 | Out
2021-07-31 | HOLD04L | Holdio Topco Limited | LONDON | Stephen Roland Browne | Calum Leslie | 2020-12-15 | MVL | 2020-12-28 | Confirm date GM resolution, notice of the liquidator's appointment and creditor's notice to claim was advertised in Gazette | 01 | D | 2021-01-04 | gdickenson | Notice was sent to courts on 18/12/20 but not advertised until 04/01/21 due to human error made by co | An email was sent to Courts on 18/12/20 to advertise the notice but the request was not completed due to human error by them-advert date was 4/1/21 |  |  | 2021-07-30 16:21 | No Breach
2021-07-31 | GOOU00M | GOL Realisations Ltd (Formerly Go Outdoors Limited) | BIRMINGHAM | Daniel James Mark Smith | Holly Savage | 2020-06-23 | ADM | 2021-03-28 | Quarterly VAT Return due from 29/11/2020 to 28/02/2021 | 01 | D | 2021-03-30 | hsavage |  | Not late due 31 March 21 |  |  | 2021-07-12 16:41 | No Breach
2021-07-31 | GOOU00M | GOL Realisations Ltd (Formerly Go Outdoors Limited) | BIRMINGHAM | Daniel James Mark Smith | Holly Savage | 2020-06-23 | ADM | 2020-12-28 | Quarterly VAT Return due from 29/08/2020 to 28/11/2020 | 01 | D | 2021-05-04 | lingo | Period 23/6/20 to 30/11/20 | VAT100 received from HMRC on 29/4/21 |  |  | 2021-07-12 16:38 | No Breach
2021-07-31 | EVAN00L | EV Opco Realisations Limited (formerly Evans Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/21 In progress, being finalised for partner review | Awaiting finalised memo to be signed off |  |  | 2021-07-06 10:15 | No Breach
2021-07-31 | EVAN01L | EV Propco Realisations Limited (formerly Evans Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/2021 In progress, being finalised for partner review | Awaiting final sign off |  |  | 2021-07-06 10:31 | No Breach
2021-07-31 | MISS01L | MS Opco Realisations Limited (formerly Miss Selfridge Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/21 In progress, being finalised for partner review | Awaiting signed dtt memo |  |  | 2021-07-06 10:58 | No Breach
2021-07-31 | MISS02L | MS Propco Realisations Limited (formerly Miss Selfridge Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/2021 In progress, being finalised for partner review | Awaiting final sign off from partner |  |  | 2021-07-06 17:30 | No Breach
2021-07-31 | OUTF01L | Outfit Retail Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/21 In progress, being finalised for partner review | Awaiting signed decision to trade memo |  |  | 2021-07-06 17:37 | No Breach
2021-07-31 | OUTF02L | Outfit Retail Properties Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/21 In progress, being finalised for partner review | Awaiting decision to trade memo |  |  | 2021-07-06 17:41 | No Breach
2021-07-31 | REDC07L | Redcastle Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/21 In progress, being finalisede for partner review | Awaiting finalised DTT memo |  |  | 2021-07-06 17:46 | No Breach
2021-07-31 | WALL01L | WR Opco Realisations Limited (formerly Wallis Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/21 In progress, being finalised for partner review | Awaiting final signed DTT memo |  |  | 2021-07-06 17:49 | No Breach
2021-07-31 | WALL02L | WR Propco Realisations Limited (formerly Wallis Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-14 | jehough | 14/01/21 In progress, being finalised for partner review | Awaiting signed DTT memo |  |  | 2021-07-06 17:55 | No Breach
2021-07-31 | SPRI02L | Sprint UK Holdings 1 Limited | LONDON | Ian Harvey Dean | Chris Holmes | 2019-06-28 | MVL | 2021-03-23 | Deliver draft final account and report to members, complete 'done' date, allowing 2 business days if first class post or 1 business day if by email | 01 | D | 2021-05-19 | gdickenson | recurred | not late |  | 2021-06-30 | 2021-07-15 14:20 | No Breach
2021-07-31 | DORO00L | DOR Opco Realisations Limited (formerly Dorothy Perkins Trading Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-07 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | D | 2021-05-21 | jehough | 14/01/21 In progress, being finalised for partner review | Awaiting finalised DTT memo |  |  | 2021-07-06 10:11 | No Breach
2021-07-31 | COVP01B | Covpress Assembly Limited | BIRMINGHAM | Matthew James Cowlishaw | Holly Savage | 2019-05-02 | CVL | 2021-06-02 | Deliver final account and notice under Rule 6.28 to members and creditors, other than opted out creditors. | 01 | D | 2021-06-18 | hsavage |  | Per HO note |  |  | 2021-07-05 13:12 | No Breach
2021-07-31 | DART04L | Mr Stephen John Dartnell | LONDON | Matthew James Cowlishaw | Holly Savage | 2011-09-15 | BKY | 2020-12-05 | Disposal of Bankrupt's records - Obtain authority from Official Receiver | 01 | D | 2021-06-24 | hsavage |  | OR delays - permission now received |  | 2020-11-05 | 2021-07-05 12:37 | No Breach
2021-07-31 | AGCL00L | A.G. Clothing Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:30 | No Breach
2021-07-31 | AGCL00L | A.G. Clothing Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:30 | No Breach
2021-07-31 | ARCA02L | Arcadia Group Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | mmmehdi |  | Completed sent same day delivery to Regtr |  |  | 2021-06-30 15:56 | No Breach
2021-07-31 | ARCA02L | Arcadia Group Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | mmmehdi | Completed sent same day delivery to hard copy creditors | Completed sent same day delivery to hard copy credit |  |  | 2021-06-30 15:56 | No Breach
2021-07-31 | ARCA04L | Arcadia Group Fashion Holdings Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:30 | No Breach
2021-07-31 | ARCA04L | Arcadia Group Fashion Holdings Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:31 | No Breach
2021-07-31 | BURT02L | BUR Trading Opco Realisations Limited (formerly Burton Trading Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:31 | No Breach
2021-07-31 | BURT02L | BUR Trading Opco Realisations Limited (formerly Burton Trading Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:31 | No Breach
2021-07-31 | BURT03L | BD Propco Realisations Limited (formerly Burton / Dorothy Perkins Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:31 | No Breach
2021-07-31 | BURT03L | BD Propco Realisations Limited (formerly Burton / Dorothy Perkins Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:31 | No Breach
2021-07-31 | DORO00L | DOR Opco Realisations Limited (formerly Dorothy Perkins Trading Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:32 | No Breach
2021-07-31 | DORO00L | DOR Opco Realisations Limited (formerly Dorothy Perkins Trading Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:34 | No Breach
2021-07-31 | EVAN00L | EV Opco Realisations Limited (formerly Evans Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:35 | No Breach
2021-07-31 | EVAN00L | EV Opco Realisations Limited (formerly Evans Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:35 | No Breach
2021-07-31 | EVAN01L | EV Propco Realisations Limited (formerly Evans Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:35 | No Breach
2021-07-31 | EVAN01L | EV Propco Realisations Limited (formerly Evans Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:35 | No Breach
2021-07-31 | MISS01L | MS Opco Realisations Limited (formerly Miss Selfridge Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:35 | No Breach
2021-07-31 | MISS01L | MS Opco Realisations Limited (formerly Miss Selfridge Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:35 | No Breach
2021-07-31 | MISS02L | MS Propco Realisations Limited (formerly Miss Selfridge Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:36 | No Breach
2021-07-31 | MISS02L | MS Propco Realisations Limited (formerly Miss Selfridge Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:36 | No Breach
2021-07-31 | OUTF01L | Outfit Retail Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:36 | No Breach
2021-07-31 | OUTF01L | Outfit Retail Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:36 | No Breach
2021-07-31 | OUTF02L | Outfit Retail Properties Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:36 | No Breach
2021-07-31 | OUTF02L | Outfit Retail Properties Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:36 | No Breach
2021-07-31 | REDC01L | Redcastle (Holdings) Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | wpackwood |  | Hand delivered to registrar |  |  | 2021-06-30 11:16 | No Breach
2021-07-31 | REDC02L | Redcastle Finance Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | wpackwood |  | Hand delivered to registrar |  |  | 2021-06-30 11:16 | No Breach
2021-07-31 | REDC04L | Redcastle (TCR) Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | wpackwood |  | Hand delivered to registrar |  |  | 2021-06-30 11:16 | No Breach
2021-07-31 | REDC05L | Redcastle (TS/TM) Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | wpackwood |  | Hand delivered to registrar |  |  | 2021-06-30 11:17 | No Breach
2021-07-31 | REDC06L | Redcastle (Freeholds) Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | wpackwood |  | Hand delivered to registrar |  |  | 2021-06-30 11:17 | No Breach
2021-07-31 | REDC07L | Redcastle Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:37 | No Breach
2021-07-31 | REDC07L | Redcastle Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:36 | No Breach
2021-07-31 | WALL01L | WR Opco Realisations Limited (formerly Wallis Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:37 | No Breach
2021-07-31 | WALL01L | WR Opco Realisations Limited (formerly Wallis Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:37 | No Breach
2021-07-31 | WALL02L | WR Propco Realisations Limited (formerly Wallis Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:37 | No Breach
2021-07-31 | WALL02L | WR Propco Realisations Limited (formerly Wallis Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report with abstract R&P to Registrar of Companies Form AM10 | 01 | D | 2021-06-29 | jehough |  | No stat breach as confirmed by QRM - posted to website and couried to CH on 29.6.21 |  |  | 2021-06-30 16:37 | No Breach
2021-07-31 | AGCL00L | A.G. Clothing Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 08:41 | No Breach
2021-07-31 | ARCA02L | Arcadia Group Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2020-12-29 | Pre appointment Quarterly VAT Return due 30/11/2020 to 29/11/2020 (Consider completion) | 01 | N | 2021-06-30 | mmmehdi | n/a | n/a |  |  | 2021-06-30 16:19 | No Breach
2021-07-31 | ARCA02L | Arcadia Group Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | mmmehdi |  | Sent first class post- not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 16:25 | No Breach
2021-07-31 | ARCA03L | Arcadia Group Brands Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | naheer |  | not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 15:48 | No Breach
2021-07-31 | ARCA04L | Arcadia Group Fashion Holdings Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 09:47 | No Breach
2021-07-31 | BURT02L | BUR Trading Opco Realisations Limited (formerly Burton Trading Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | not late as confirmed by RK |  |  | 2021-07-06 10:05 | No Breach
2021-07-31 | BURT03L | BD Propco Realisations Limited (formerly Burton / Dorothy Perkins Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 10:09 | No Breach
2021-07-31 | DORO00L | DOR Opco Realisations Limited (formerly Dorothy Perkins Trading Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 10:13 | No Breach
2021-07-31 | EVAN00L | EV Opco Realisations Limited (formerly Evans Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 10:17 | No Breach
2021-07-31 | EVAN01L | EV Propco Realisations Limited (formerly Evans Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 10:34 | No Breach
2021-07-31 | MISS01L | MS Opco Realisations Limited (formerly Miss Selfridge Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 13:51 | No Breach
2021-07-31 | MISS02L | MS Propco Realisations Limited (formerly Miss Selfridge Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 17:33 | No Breach
2021-07-31 | OUTF01L | Outfit Retail Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 17:39 | No Breach
2021-07-31 | OUTF02L | Outfit Retail Properties Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 17:43 | No Breach
2021-07-31 | PROJ00B | Project Angel Bidco Limited | BIRMINGHAM | Daniel James Mark Smith | Becky Withington | 2021-06-01 | ADM | 2021-06-04 | Confirm Administrators have been validly appointed by obtaining legal advice (place filenote or legal confirmation on file) | 01 | D | 2021-06-30 | mmmehdi | We have requested for a report on the validity from the lawyers but will take a couple of weeks to come back as its a complicated case | We have requested for a report on the validity from the lawyers but will take a couple of weeks to come back as its a complicated case |  |  | 2021-07-30 16:19 | No Breach
2021-07-31 | REDC04L | Redcastle (TCR) Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | wpackwood |  | Not Late - due date confirmed by Renee Kingwell |  |  | 2021-07-01 07:37 | No Breach
2021-07-31 | REDC05L | Redcastle (TS/TM) Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | wpackwood |  | Not Late - due date confirmed by Renee Kingwel |  |  | 2021-07-01 07:37 | No Breach
2021-07-31 | REDC06L | Redcastle (Freeholds) Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | wpackwood |  | Not Late - due date confirmed by Renee Kingwel |  |  | 2021-07-01 07:37 | No Breach
2021-07-31 | REDC07L | Redcastle Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | COnfirmed late by RK |  |  | 2021-07-06 17:48 | No Breach
2021-07-31 | TOPS02L | Top Shop/Top Man Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-27 | Deliver six monthly progress report to creditors, by posting to website and any creditors who have requested hard copies - Rule 18.6 | 01 | D | 2021-06-30 | naheer | Uploaded to creditor portal on 29 June 2021 | Hardcopy requestors issued 30 June 2021 |  |  | 2021-06-30 09:50 | No Breach
2021-07-31 | TOPS02L | Top Shop/Top Man Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | naheer |  | not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 15:50 | No Breach
2021-07-31 | TOPS03L | TS Wholesale Realisations Limited (Formerly Top Shop/Top Man (Wholesale) Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | naheer |  | not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 16:01 | No Breach
2021-07-31 | TOPS04L | TS (Germany) Realisations Limited (Formerly Top Shop/Top Man (Germany) Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | naheer |  | not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 15:53 | No Breach
2021-07-31 | TOPS05L | TS (Trinity) Realisations Limited (Formerly Top Shop/Top Man (Trinity) Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | naheer |  | not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 15:57 | No Breach
2021-07-31 | TOPS06L | Top Shop / Top Man Properties Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | naheer |  | not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 16:02 | No Breach
2021-07-31 | VITA00B | Vital Infrastructure Asset Management (VIAM) Ltd | BIRMINGHAM | Daniel James Mark Smith | Becky Withington | 2021-06-01 | ADM | 2021-06-04 | Confirm Administrators have been validly appointed by obtaining legal advice (place filenote or legal confirmation on file) | 01 | D | 2021-06-30 | mmmehdi | We have instructed lawyers to carry out validity report | We have requested for a report on the validity from the lawyers but will take a couple of weeks to come back as its a complicated case |  |  | 2021-07-30 16:19 | No Breach
2021-07-31 | WALL01L | WR Opco Realisations Limited (formerly Wallis Retail Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 17:55 | No Breach
2021-07-31 | WALL02L | WR Propco Realisations Limited (formerly Wallis Retail Properties Limited) | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | jehough |  | Not late as confirmed by RK |  |  | 2021-07-06 17:57 | No Breach
2021-07-31 | ZOOM00L | Zoom.co.uk Limited | BIRMINGHAM | Matthew David Smith | Joe Barry | 2020-11-30 | ADM | 2021-06-29 | Quarterly VAT Return due 30/11/2020 to 29/05/2021 | 01 | D | 2021-06-30 | naheer |  | not late, due date confirmed by Renee Kingwell’ |  |  | 2021-06-30 15:54 | No Breach
2021-07-31 | POUN00D | Poundworld Retail Limited | BIRMINGHAM | Daniel Francis Butters | Holly Savage | 2018-06-11 | ADM | 2020-12-13 | Pay unclaimed/returned dividend to ISA - Form CAU103 | 01 | D | 2021-07-01 | nsunner | Completed | Re-issue delays |  | 2020-06-18 | 2021-07-06 12:20 | No Breach
2021-07-31 | POUN00D | Poundworld Retail Limited | BIRMINGHAM | Daniel Francis Butters | Holly Savage | 2018-06-11 | ADM | 2020-12-24 | Pay unclaimed/returned dividend to ISA - Form CAU103 | 01 | D | 2021-07-01 | nsunner | Completed | Re-issue delays |  | 2020-06-18 | 2021-07-06 12:21 | No Breach
2021-07-31 | 135000Y | 1350 Eye Street Limited | GUERNSEY | Alex Adam | Oliver Lythgoe |  | MVL | 2021-03-28 | Completed TOP approved by relevant parties and filed on CM pre-engagement folder together with PAP briefing note | 01 | D | 2021-07-02 | melaanderson |  | late update of diaries |  |  | 2021-07-02 13:06 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-06-25 | Circulate written resolutions to Members if not being dealt with by company | 01 | D | 2021-07-02 | cjleslie |  | Not formally instructed until 2 July 2021 |  |  | 2021-07-09 08:49 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-04 | Register if necessary and conduct pension search on PPF website (follow section link) NOT N/A | 01 | D | 2021-07-05 | lfhenderson | No scheme found | 4 July a Sunday, complete Monday 5th |  |  | 2021-07-05 17:25 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-04 | Conduct pension search on gov.uk website (follow section link) NOT N/A | 01 | D | 2021-07-05 | lfhenderson |  | 4 July a Sunday. Search made on Monday 5th |  |  | 2021-07-05 17:24 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-02 | Notify Insolvency Service of redundancies | 01 | D | 2021-07-05 | lfhenderson |  | Late appt on 2 July |  |  | 2021-07-05 17:26 | No Breach
2021-07-31 | TOTA06D | Total Asset Limited | LEEDS | Daniel Francis Butters | Becky Withington | 2011-10-03 | CVL | 2021-07-05 | Deliver annual progress report to creditors and members via website and to any creditor who has requested hard copy S104A | 01 | D | 2021-07-06 | bwithington |  | Portal set up and notified to creditors on 6/7. Not late. |  |  | 2021-07-06 09:28 | No Breach
2021-07-31 | TOTA06D | Total Asset Limited | LEEDS | Daniel Francis Butters | Becky Withington | 2011-10-03 | CVL | 2021-07-05 | Send annual progress report to previously unknown creditors | 01 | D | 2021-07-06 | bwithington |  | Portal set up and notified to creditors on 6/7. Not late. |  |  | 2021-07-06 09:29 | No Breach
2021-07-31 | TOTA06D | Total Asset Limited | LEEDS | Daniel Francis Butters | Becky Withington | 2011-10-03 | CVL | 2021-07-05 | Send annual progress report to Registrar with covering LIQ03 | 01 | D | 2021-07-06 | bwithington |  | Report approved after last post. Report sent 6/7. |  |  | 2021-07-06 09:29 | No Breach
2021-07-31 | SUKR01C | SUK Retail Limited | BIRMINGHAM | Richard Michael Hawes | Holly Savage | 2019-03-18 | ADM | 2020-11-13 | Pay unclaimed/returned dividend to ISA - Form CAU103 | 01 | N | 2021-07-07 | nsunner | Reissue not paying to ISA | . |  |  | 2021-07-07 15:39 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-06-29 | Register if necessary and conduct pension search on PPF website (follow section link) NOT N/A | 01 | D | 2021-07-08 | marowe | No scheme found | Appointed 06/07/2021 |  |  | 2021-07-29 12:13 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-06-29 | Conduct pension search on gov.uk website (follow section link) NOT N/A | 01 | D | 2021-07-08 | marowe | No scheme found | Appointed 06/07/2021 |  |  | 2021-07-29 12:13 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-04 | Issue redundant employees with redundancy letter and pack | 01 | D | 2021-07-08 | lfhenderson |  | Didn't receive confirmed EE data until late 7th |  |  | 2021-07-08 08:18 | No Breach
2021-07-31 | A1HI00M | A1 Hire And Sales Limited | MANCHESTER | Daniel James Mark Smith | Heather Hughes | 2021-06-30 | MVL | 2021-05-31 | Quarterly VAT Return due 30/06/2021 to 30/04/2021 | 01 | N | 2021-07-09 | heahughes | NA prior to apt | NA |  |  | 2021-07-09 10:09 | No Breach
2021-07-31 | PROJ00B | Project Angel Bidco Limited | BIRMINGHAM | Daniel James Mark Smith | Becky Withington | 2021-06-01 | ADM | 2021-06-19 | Deadline for receipt of Statement of Affairs and if applicable all statements of concurrence. Mark as Done when received. If extension granted, mark N/A and recur this line to new deadline. | 01 | D | 2021-07-09 | mmmehdi | Extenson granted to 9 July 2021- received. Letter granting extension on file. | Can't recur this line so I have commented here to show why its not late as extension has been granted |  |  | 2021-07-19 15:08 | No Breach
2021-07-31 | VEIN01L | VE Interactive Limited | LONDON | Daniel Francis Butters | John Lynch | 2019-04-19 | CVL | 2021-06-28 | Pay unclaimed/returned dividend to ISA - Form CAU103 | 01 | N | 2021-07-12 | sflafferty | No Unclaimed Divs | Assisting with backlog |  |  | 2021-07-12 10:18 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-09 | Issue notice to Courts Advertising to advertise liquidators' appointment in the Gazette (must be advertised within 14 days of appointment) | 01 | D | 2021-07-15 | hsavage |  | Centrebind appt unable to send until deemed decisi |  |  | 2021-07-15 14:51 | No Breach
2021-07-31 | BOWE08B | Bowen Travel Transportation Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Deliver annual progress report to creditors and members via website and to any creditor who has requested hard copy S104A | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:58 | No Breach
2021-07-31 | BOWE08B | Bowen Travel Transportation Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to previously unknown creditors | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:58 | No Breach
2021-07-31 | BOWE08B | Bowen Travel Transportation Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to Registrar with covering LIQ03 | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:58 | No Breach
2021-07-31 | JEFF02B | Jeffs Coaches Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to previously unknown creditors | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:40 | No Breach
2021-07-31 | JEFF02B | Jeffs Coaches Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Deliver annual progress report to creditors and members via website and to any creditor who has requested hard copy S104A | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:40 | No Breach
2021-07-31 | JEFF02B | Jeffs Coaches Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to Registrar with covering LIQ03 | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:40 | No Breach
2021-07-31 | LFBO01B | L.F. Bowen Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Deliver annual progress report to creditors and members via website and to any creditor who has requested hard copy S104A | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:34 | No Breach
2021-07-31 | LFBO01B | L.F. Bowen Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to previously unknown creditors | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:34 | No Breach
2021-07-31 | LFBO01B | L.F. Bowen Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to Registrar with covering LIQ03 | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:34 | No Breach
2021-07-31 | MOSE04B | Moseley Group (P.S.V) Plc | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Deliver annual progress report to creditors and members via website and to any creditor who has requested hard copy S104A | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:31 | No Breach
2021-07-31 | MOSE04B | Moseley Group (P.S.V) Plc | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to previously unknown creditors | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:31 | No Breach
2021-07-31 | MOSE04B | Moseley Group (P.S.V) Plc | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to Registrar with covering LIQ03 | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:31 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-16 | Confirm date Notice of appointment was advertised in Gazette | 01 | D | 2021-07-19 | hsavage |  | Centerbind appt - done within 7 days of deemed dec |  |  | 2021-07-22 10:01 | No Breach
2021-07-31 | SWGO00L | SWG Realisations Limited (formerly SW Golf Limited) | LONDON | Daniel James Mark Smith | Holly Savage | 2018-10-12 | ADM | 2021-04-08 | Pay unclaimed/returned dividend to ISA - Form CAU103 | 01 | D | 2021-07-19 | nsunner | Cheques reissued Feb 2021 | . |  | 2020-10-28 | 2021-07-20 12:23 | No Breach
2021-07-31 | UKSE00G | UK Secured Finance Fund Plc | GUERNSEY | Alex Adam | Andy Wood | 2015-06-10 | WUC | 2021-03-21 | Pay any Tax liability Year 5 | 01 | D | 2021-07-19 | melaanderson |  | late |  |  | 2021-07-19 10:12 | No Breach
2021-07-31 | WOOT02B | Woottens Luxury Travel Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to previously unknown creditors | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:28 | No Breach
2021-07-31 | WOOT02B | Woottens Luxury Travel Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Deliver annual progress report to creditors and members via website and to any creditor who has requested hard copy S104A | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:28 | No Breach
2021-07-31 | WOOT02B | Woottens Luxury Travel Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to Registrar with covering LIQ03 | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:28 | No Breach
2021-07-31 | YORK09B | York Bros (Northampton) Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to previously unknown creditors | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:25 | No Breach
2021-07-31 | YORK09B | York Bros (Northampton) Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Deliver annual progress report to creditors and members via website and to any creditor who has requested hard copy S104A | 01 | D | 2021-07-19 | naheer |  | NOT LATE NO HARDCOPY REQUESTORS, OCM ARE AWARE |  |  | 2021-07-20 09:24 | No Breach
2021-07-31 | YORK09B | York Bros (Northampton) Limited | BIRMINGHAM | Matthew James Cowlishaw | John Lynch | 2013-05-21 | CVL | 2021-07-18 | Send annual progress report to Registrar with covering LIQ03 | 01 | D | 2021-07-19 | naheer |  | NOT LATE, NO HARD COPY REQUESTORS OCM AWARE |  |  | 2021-07-20 09:25 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-14 | Send notice of appointment and statutory filings as applicable to Registrar of Companies (must be filed within 14 days of date of appointment) | 01 | D | 2021-07-20 | hsavage |  | Centerbind appt done within 7 days of deemed appt |  |  | 2021-07-20 15:54 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Deliver notice of Appointment and change of registered office to Registrar of Companies Form AM01 / AD01 | 01 | D | 2021-07-21 | Mayatta.Daramy |  | Completed |  |  | 2021-07-23 08:44 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Send notice of Appointment to Debenture Holders and secured creditors | 01 | D | 2021-07-21 | Mayatta.Daramy |  | Completed |  |  | 2021-07-23 08:58 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Date advert published in Gazette Rule 3.27 | 01 | D | 2021-07-21 | Mayatta.Daramy | Completed | Completed |  |  | 2021-07-27 16:16 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-09 | Send letter re appointment to Members | 01 | D | 2021-07-21 | hsavage |  | Centerbind appt - done within 7 days |  |  | 2021-07-21 17:25 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-09 | Notify all current and former directors of appointment (at both company and private addresses) including directors' questionnaire (for investigation purposes). Include advice on s216 implications. | 01 | D | 2021-07-21 | hsavage |  | Centerbind appt - done within 7 days |  |  | 2021-07-21 17:25 | No Breach
2021-07-31 | STOBA0001I | Stobart Air Services (UK) Ltd | BIRMINGHAM | Stephen Roland Browne | Holly Savage | 2021-07-02 | CVL | 2021-07-09 | Deliver Initial letter to creditors, and post to the case website, re appointment and decision procedure to fix remuneration / form a committee | 01 | D | 2021-07-21 | hsavage |  | Centerbind appt - done within 7 days |  |  | 2021-07-21 17:25 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Send notice of Appointment to HP/Lease creditors | 01 | D | 2021-07-22 | Mayatta.Daramy |  | Completed |  |  | 2021-07-23 09:06 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Send notice of appointment to Company's bankers/solicitors/previous insurers/other professional advisors | 01 | D | 2021-07-22 | Mayatta.Daramy | Sent to relevant party | Completed |  |  | 2021-07-23 08:49 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Issue notice of appointment to all creditors including employees (with notification of website address) | 01 | D | 2021-07-22 | Mayatta.Daramy | Completed | Completed |  |  | 2021-07-23 08:49 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Confirm signed decision to trade (or not) memo is on filed on CM | 01 | N | 2021-07-23 | Mayatta.Daramy | DTT memo from previous appt still valid, no changes | Not applicable |  |  | 2021-07-23 09:34 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Consider which director will be asked/agree to prepare the SoA. Send standard letter to identified director | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Completed |  |  | 2021-07-23 09:01 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | If contentious, provide statements of concurrence to relevant persons. Send standard letter to concurring directors | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 09:02 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Issue notice of Appointment to Supervisor of CVA | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 08:50 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Issue notice of Appointment to those who have exercised a lien or any known enforcement officer | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 08:50 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Issue notice to one or more relevant persons to deliver a statement of affairs within 11 days of receipt of notice. Para 47 Rule 3.29 | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 09:03 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | If decision made to dispense of requirement to prepare SoA, document reason and file on CM | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 09:04 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Send notice of Appointment to Provisional Liquidator | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicale | Not applicable |  |  | 2021-07-23 08:58 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Send notice of Appointment to Company Para 46 Rule 3.27 | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 09:02 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-09 | Confirm Administrators have been validly appointed by obtaining legal advice (place filenote or legal confirmation on file) | 01 | N | 2021-07-23 | Mayatta.Daramy | Court appointment | Not applicable |  |  | 2021-07-23 09:32 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Send notice of Appointment to Petitioning Creditors | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 08:47 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-07 | Request H&S report of commercial properties/communal areas | 01 | N | 2021-07-23 | Mayatta.Daramy | completed in the previous admin and no changes. Insurance from previous admin has been transferred to new appt | Not applicable |  |  | 2021-07-23 09:30 | No Breach
2021-07-31 | PARKP0001I | Park Place Plaza Ltd | BIRMINGHAM | David Philip Soden | Robert Luff | 2021-07-06 | ADM | 2021-07-13 | Send notice of Appointment to Receiver or Administrative Receiver | 01 | N | 2021-07-23 | Mayatta.Daramy | Not Applicable | Not applicable |  |  | 2021-07-23 08:47 | No Breach
2021-07-31 | SUNWI0001I | Sun Wise (UK) Co., Ltd | BIRMINGHAM | David Philip Soden | Robert Woolsey | 2021-07-02 | FRC | 2021-07-08 | Notice of appointment to Registrar of Companies by appointor - RM01 | 01 | D | 2021-07-23 | vmistry |  | Finding relevent property charge code |  |  | 2021-07-23 15:45 | No Breach